## Gantt
www.excelintellect.com
Gantt Chart
Enter tasks, start dates and working days. The timeline draws itself.
Timeline starts | 2026-11-02
Weekend code (1 = Sat-Sun, 7 = Fri-Sat) | 1
[6 empty] | 2026-11-02 | [6 empty] | 2026-11-09 | [6 empty] | 2026-11-16 | [6 empty] | 2026-11-23 | [6 empty] | 2026-11-30 | [6 empty] | 2026-12-07 | [6 empty] | 2026-12-14 | [6 empty] | 2026-12-21
Task | Owner | Start | Work days | End | % done | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
Project brief | Owner A | 2026-11-02 | 3 | 2026-11-04 | 100%
Requirements | Owner B | 2026-11-05 | 5 | 2026-11-11 | 80%
Design | Owner C | 2026-11-12 | 8 | 2026-11-23 | 40%
Build | Owner B | 2026-11-20 | 15 | 2026-12-10 | 10%
Testing | Owner D | 2026-12-11 | 6 | 2026-12-18 | 0%
Launch | Owner A | 2026-12-21 | 2 | 2026-12-22 | 0%

## Instructions
www.excelintellect.com
How to use: Gantt Chart
Free template from Excel Intellect
Steps
1 | Set the timeline start date in cell B8. The grid covers 56 days from that date.
2 | Choose your weekend pattern in cell B9: 1 for Saturday and Sunday, 7 for Friday and Saturday, or 11 for Sunday only.
3 | Enter each task with an owner, start date, working days and % done. The end date skips weekends.
4 | Teal bars show the plan and dark bars show progress. Grey columns are weekends. Public holidays are not included.
Color guide
Pale yellow with blue text: type here. Sample entries are examples, so replace them.
White: formula. It updates by itself, so leave it as is.
Pale teal: totals and results.
Functions used
WORKDAY.INTL, IF, AND, OR, WEEKDAY
Using this file
No macros. Formulas are unlocked, so you can change anything.
If Excel opens the file in Protected View, select Enable Editing.
For Google Sheets, upload the file to Drive and open it with Google Sheets. Check the layout after import.
Free for personal and business use. Please do not resell this file.
Figures are examples only. Check results before you rely on them.
More free formulas, templates and tools: www.excelintellect.com